## Sheet1
Gantt Chart | Highschool Student Simulator
By Tahu Bulat Dadakan
Activity |  | PIC | Week
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Phase 1 ¦ Planning & Requirements
Define game objectives and scope | Identify key mechanics | Daniel Prawira | bar: Week 9
| Design initial wireframes and UI concepts | Kayla Fakhira | bar: Week 9
| Set up project management tools and Agile workflow | Syedha Audry timothy Piri | bar: Week 3
| Assign roles and responsibilities | Shevchenko Saviour Matthew Poluan | bar: Week 2
| Create a backlog of features | Syedha Audry Timothy Piri | bar: Week 3
Phase 2 ¦ Developing Core Functionality
Student Life System | Implement character attributes | Daniel Prawira | bar: Week 14
| Create daily schedule mechanics | Daniel Prawira | bar: Week 14
| Add interactions with NPCs | Daniel Prawira | bar: Week 14
Studying & Exams | Implement study system | Daniel Prawira | bar: Week 14
| Develop quiz/exam system with different difficulty levels | Daniel Prawira | bar: Week 14
School Activities & Events | Implement Part-time jobs | Daniel Prawira | bar: Week 14
| Implement extracurricular activities | Daniel Prawira | bar: Week 14
| Add choices affecting reputation and academic performance | Daniel Prawira | bar: Week 14
UI & Progression System | Design user-friendly HUD | Kayla Fakhira | bar: Week 13
Arts | Main Menu Background | Kayla Fakhira | bar: Week 14
| School Design | Kayla Fakhira | bar: Week 14
| Player's Home Design | Kayla Fakhira | bar: Week 14
| Minigames Background | Kayla Fakhira | bar: Week 14
Music | Main menu music | Dave Geraldo Jonathan Koro | bar: Week 15
| School Music | Dave Geraldo Jonathan Koro | bar: Week 15
| Minigame music | Dave Geraldo Jonathan Koro | bar: Week 15
Phase 3 ¦ Testing & Debugging
Playtesting | Internal playtesting | Joel Daniel Mark Wenas
| Identify gameplay bugs | Joel Daniel Mark Wenas | bar: Week 15
| Optimize performance & UI | Kayla Fakhira
| beta testing & feedback | Joel Daniel Mark Wenas | bar: Week 15
Phase 4 ¦ Finalization & Documentation
UI | Polish UI | Kayla Fakhira
Music | Polish Music | Dave Geraldo Jonathan Koro | bar: Week 15
Documentation | Team Contract | Shevchenko Saviour Matthew Poluan | bar: Week 9
| Contract with Client | Shevchenko Saviour Matthew Poluan | bar: Week 9
| Proposal | Shevchenko Saviour Matthew Poluan | bar: Week 9
| Project Planner | Shevchenko Saviour Matthew Poluan | bar: Week 9 to Week 12
| Software Requirements Specification | Shevchenko Saviour Matthew Poluan | bar: Week 9 to Week 15