## Sheet1
Activity |  | PIC | 2025-04-01
|  |  | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
Dokumentasi | Membuat Revisi Gantt Chart Planner | Shevchenko
| Membuat Burndown chart | Shevchenko
| Membuat SRS | Shevchenko
| Membuat Game Design Document | Shevchenko
Diagrams | Membuat Use case diagram | Shevchenko
| Membuat state diagram | Shevchenko
| Membuat activity Diagram | Shevchenko
| Membuat Class Diagram | Daniel Prawira
Game Coding | School Classes Feature | Daniel Prawira | bar: 2025-04-01 16 to 2025-04-01 18
| Gym Feature | Daniel Prawira | bar: 2025-04-01 19 to 2025-04-01 20
| Part-Time Job Feature | Daniel Prawira | bar: 2025-04-01 19 to 2025-04-01 20
| Player Stats | Daniel Prawira | bar: 2025-04-01 19 to 2025-04-01 20
| Game ending Condition | Daniel Prawira
| Game Losing Condition | Daniel Prawira
Musik | Main Menu Music | Dave Geraldo | bar: 2025-04-01 25
| School Hall Music | Dave Geraldo | bar: 2025-04-01 25
| Minigame Music | Dave Geraldo | bar: 2025-04-01 25
Arts | School Background | Kayla Fakhira | bar: 2025-04-01 16
| Home Background | Kayla Fakhira | bar: 2025-04-01 16
| Gym Background | Kayla Fakhira | bar: 2025-04-01 16
| Convenience Store Background | Kayla Fakhira | bar: 2025-04-01 16
| City Background | Kayla Fakhira | bar: 2025-04-01 16
Testing | Open Testing | Joel | bar: 2025-04-01 26 to 2025-04-01 27
| Testing Report | Joel | bar: 2025-04-01 28